## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
1 | Pass/fail | As a student I want to know whether the subjects are passed or not So that I will attend the makeup course in the next semester or not | very high | 1 | The system needs to judge whether the user has passed the subject based on the user's single subject score |  | 3.27 | 3.31
2 | GPA the user have obtained (single subject) | As a student I want to check my GPA of every subject on this system So that I can know about GPA I have got in each subject | very high | 1 | The system needs to calculate the user's GPA based on the user's single subject grades |  | 3.27 | 3.31
3 | GPA and average marks | As a student I want to know my marks and inquire the GPA and average marks of all my studied subjects in the system So that I can understand my strengths and weaknesses in study and my life plan after undergraduate (employment or master study). | very high | 1 | The system needs to calculate the user's GPA and grade point average based on the user's grades in all subjects |  | 3.27 | 3.31
4 | Record skills the user have learned | As a student I want to record the skills (include software,language,hardware,knowledge and others) I have learned So that I can be able to know how many skills I have acquired during my four years in college, and what skills I lacked | very high | 1 | User can write skills by himself by clicking the button "write". |  | 3.27 | 3.31
5 | Read skills the user have learned | As a student I want to read the skills I have recorded So that I can use the information to write a resume or introduce myself to others | very high | 1 | User can read skills which is already existed by clicking the button "load". |  | 3.27 | 3.31
6 | Modify skills the user have learned | As a student I want to modify the skills where I have recorded in the system So that it can prevent me from making typing errors when I perform the recording function | very high | 1 | User can modify skills which is already existed by clicking the button "Modify". |  | 3.27 | 3.31
7 | Documenting achievements | As a student I want to have a platform to record my achievements or honors during my college years So that I can easily look up my achievements for my master's program or PhD program and write up relevant documents | very high | 1 | User can write achievements by himself by clicking the button "Add achievement". |  | 3.27 | 3.31
8 | Revision of the achievements | As a student user I wnat to be able to modify what I have entered into the system when I record my achievements So that I do not have to worry about recording the wrong information about my achievements and can modify the specific designation of my achievements according to the requirements of the program I am applying for | very high | 1 | User can modify achievements which is already existed by clicking the button "Modify Achievement".Input old achievement in the corresponding text box and input new achievement in the correponding text box. |  | 3.27 | 3.31
9 | Deleting achievements | As a student user I want to that I could always delete the achievements that have been recorded into the system So that I could do some filtering at the end of the semester or at graduation based on the importance of these achievements and delete those that are not necessary to appear on my resume | very high | 2 | User can delete achievements by clicking the button"Remove Achievement" |  | 4.3 | 4.14
10 | List achievements | As a student user I want to check all my achievements So that I can view all my honors in a specific area without having to look for them | very high | 2 | User can see all the achievements in the blank board |  | 4.3 | 4.14
11 | Record and query volunteer experience and roles undertaken | As a student I want to record my volunteer activities So that I can better arrange my volunteer plan, check how many volunteer hours I had got and how many volunteer hoursI need to meet the standard. | very high | 2 | User can write credits by himself by clicking the button "Add" and input experience in the corresponding text box User can write credits by himself by clicking the button "Add" and input roles in the corresponding text box User can check what they add in the blank board |  | 4.3 | 4.14
12 | Edit volunteer experience | As a student I want to revise my volunteer activities So that it can prevent me from making typing errors when I perform the recording function | very high | 2 | User can edit by himself by clicking the button "edit" and revise something in the corresponding text box |  | 4.3 | 4.14
13 | Edit class roles undertaken | As a student I want to revise my class roles undertaken So that it can prevent me from making typing errors when I perform the recording function | very high | 2 | User can edit by himself by clicking the button "edit" and revise something in the corresponding text box |  | 4.3 | 4.14
14 | Edit club roles undertaken | As a student I want to revise my club roles undertaken So that it can prevent me from making typing errors when I perform the recording function | very high | 2 | User can edit by himself by clicking the button "edit" and revise something in the corresponding text box |  | 4.3 | 4.14
15 | Moral score computing | As a student I want to know the influence my current experience has on my moral education score, so I hope to get the moral education score added for each experience (volunteer jobs, roles undertaken and research experience or other achievements, and sum these scores to get the total score, and finally show it to me for my inquiry. So that I can get the moral score instead of adding the credits myself. | very high | 2 | User can click the button "compute" so that the moral education score is displyed on the screen |  | 4.3 | 4.14
16 | Login the user account | As a student I want to have my own ID in this system So that I can query my own academic information. | high | 2 | User must enter the specified account and password on the login page. Otherwise, the login fails |  | 4.17 | 4.28
17 | Record classroom of every subject | As a student I want to record the classroom where I have classes So that I can attend classes on time to avoid being late | high | 3 | User can write classrooms by himself by clicking the button "Add" and input something in the corresponding text box |  | 4.17 | 4.28
18 | Read classroom of every subject | As a student I want to read the classroom where I have recorded in the system So that I can check which classroom I will be in before the class starts | high | 3 | User can read information about classrooms which is already existed by clicking the button "Exit".Do not make any changes and just read information in the context box |  | 4.17 | 4.28
19 | Modify classroom of every subject | As a student I want to modify the classroom where I have recorded in the system So that it can prevent me from making typing errors when I perform the recording function | high | 3 | User can modify information about classrooms which is already existed by clicking the button "Exit" and Re-enter the content that the user wants to modify in the corresponding text box |  | 4.17 | 4.28
20 | Record time of every subject | As a student I want to record the exact time of each class So that I won’t be late for class or miss the class | high | 3 | User can write schooltime by himself by clicking the button "Add" and input something in the corresponding text box |  | 4.17 | 4.28
21 | Read time of every subject | As a student I want to read the exact time of each class which I have recorded So that I can check When do I need to be in the classroom | high | 3 | User can read schooltime which is already existed by clicking the button "Exit".Do not make any changes and just read information in the context box |  | 4.17 | 4.28
22 | Modify time of every subject | As a student I want to modify the time where I have recorded in the system So that it can prevent me from making typing errors when I perform the recording function | high | 3 | User can modify schooltime which is already existed by clicking the button "Exit" and Re-enter the content that the user wants to modify in the corresponding text box |  | 4.17 | 4.28
23 | Volunteer time computing | As a student I want to check how much time I spend on volunteer work So that I can balance my study and volunteer work. | high | 3 | User can check corresponding information on the blank board |  | 4.17 | 4.28
24 | Roles undertaken rank segmentation | As a student I want to know the rank of my roles that I undertaken in different classes or clubs So that I can have an idea of how the score is calculated. | high | 3 | User can check corresponding information on the blank board |  | 4.17 | 4.28
25 | Record teacher's name of every subject into system | As a student I want to record the recognized teacher's name for each course So that it's convenient to ask the teacher for advice on the problems I encounter | medium | 4 | User can write teachers' name by himself by clicking the button "Add" and input something in the corresponding text box |  | 5.1 | 5.12
26 | Read teacher's name of every subject into system | As a student I want to read the recognized teacher's name for each course which I have recorded So that it's convenient for user to check teacher's name | medium | 4 | User can read teachers' name which is already existed by clicking the button "Exit".Do not make any changes and just read information in the context box |  | 5.1 | 5.12
27 | Modify teacher's name of every subject into system | As a student I want to modify the recognized teacher's name for each course which I have recorded So that it can prevent me from making typing errors when I perform the recording function | medium | 4 | User can modify techchers' name which is already existed by clicking the button "Exit" and Re-enter the content that the user wants to modify in the corresponding text box |  | 5.1 | 5.12
28 | Record semester which the subject is held | As a student I want to record which semester some subject will be delivered So that I can review the class I have taken and preview the class I haven’t | medium | 4 | User can write semester by himself by clicking the button "Add" and input something in the corresponding text box |  | 5.1 | 5.12
29 | Read semester which the subject is held | As a student I want to read which semester some subject will be delivered So that it can make it convenient for me to check the courses I have not learned, and help me to have targeted preview during the holiday | medium | 4 | User can read semester which is already existed by clicking the button "Exit".Do not make any changes and just read information in the context box |  | 5.1 | 5.12
30 | Modify semester which the subject is held | As a student I want to modify the semester which the subject is held where I have recorded in the system So that it can prevent me from making typing errors when I perform the recording function | medium | 4 | User can modify semester which is already existed by clicking the button "Exit" and Re-enter the content that the user wants to modify in the corresponding text box |  | 5.1 | 5.12
31 | Record credits for each subject | As a student of international school of BUPT, I want to record the credit each module accounts for. So that I can attribute the attention to different modules and this material can also provide a reference for MSc’s major selection. | medium | 4 | User can write credits by himself by clicking the button "Add" and input something in the corresponding text box |  | 5.1 | 5.12
32 | Read credits for each subject | As a student of international school of BUPT, I want to record the credit each module accounts for. So that it can provide a reference for MSc’s major selection because credits can reflect the characteristics of my undergraduate major | medium | 4 | User can read credits which is already existed by clicking the button "Exit".Do not make any changes and just read information in the context box |  | 5.1 | 5.12
33 | Modify credits for each subject | As a student I want to modify the credits for each subject where I have recorded in the system So that it can prevent me from making typing errors when I perform the recording function | medium | 4 | User can modify credits which is already existed by clicking the button "Exit" and Re-enter the content that the user wants to modify in the corresponding text box |  | 5.1 | 5.12
34 | Display schedule | As a student I want to see my class schedule on the main page So that I can easily check my class schedule anytime, anywhere | low | 4 | User can see class schedule on the main page |  | 5.1 | 5.12
35 | Show transcript | As a student I want to have a transcript that lists my grades for all subjects So that I can easily check my grades | low | 4 | User can see your transcript |  | 5.1 | 5.12
36 | Check to-be-carried plan on the learning system | As an undergraduate student I want to be able to record and check my to-be-carried plan on the learning system So that I can effectively plan and manage my future courses and academic progress | low | 4 | 1.The system should allow user to specify the desired semester or academic period for each module in my plan 2.The system should provide user with a clear overview of my planned modules, including the module names, assigned semesters, and any additional information or requirements associated with each module |  | 5.1 | 5.12